## Project Info Entity
Project ID | Forecast Start Date | Forcast End Date | Customer | Project Name | Project Manager | Budget Hours | Budget Materials
10642 | 2018-01-02 | 2018-04-02 | CAE | GT30 Compressor Development-FY17 additional scope | Gabriel Taraboulsi | 1440 | 10000
10480 | 2018-05-06 | 2018-08-04 | CAE | Manufacturing Support for 5 Year Plan | Allen Ennis | 2280 | 57000
10490 | 2018-06-05 | 2018-09-03 | GE | Casting Remastering (Blade & Vane) | Joshua Senechal | 3058 | 195000
10604 | 2018-03-25 | 2018-06-23 | GE | DOC into industrial Trent | Gabriel Taraboulsi | 308 | 30000
10562 | 2018-09-21 | 2018-12-20 | Boeing | Trent Cost Reduce Casing-Integration Mechanical Integrity | Mihai Jivan | NULL | 300000
10607 | 2019-01-08 | 2019-04-08 | Pratt & Whitney | Industrial Trent PhV liner re-design | Gabriel Taraboulsi | NULL | 25000
10699-1 | 2019-04-20 | 2019-07-19 | Pratt & Whitney | MRL EF Industrialisation MTB Compressors Blades | Allen Ennis | 710 | 19000
10700-1 | 2019-03-16 | 2019-06-14 | Airbus | MRL FY18 EF Industrialisation MTB Compressors HP Vanes (PDE/V&V/M&M Portions) | Allen Ennis | 801 | 61000
10698-1 | 2019-02-05 | 2019-05-06 | Airbus | MRL FY18 EF Industrialisation MTB CMP BV RR to Jamo | Allen Ennis | 383 | 120000

## Project Budget Entity
Project ID | Resource Type | Month Date | Budget Hours | Budget Material | Actual Budget Hours | Actual Budget Materials
10642 | Project | 2018-01-01 | 240 |  | 260
10642 | Project | 2018-02-01 | 240 |  | 200
10642 | Project | 2018-03-01 | 240 |  | 200
10642 | Engineering | 2018-01-01 | 240 |  | 300
10642 | Engineering | 2018-02-01 | 120 |  | 200
10642 | Engineering | 2018-03-01 | 0 |  | 50
10642 | Operations | 2018-01-01 | 0 |  | 0
10642 | Operations | 2018-02-01 | 120 | 5000 | 120 | 3000
10642 | Operations | 2018-03-01 | 240 | 5000 | 200 | 5000
10480 | Project | 2018-05-06 | 240 |  | 240
10480 | Project | 2018-06-06 | 240 |  | 240
10480 | Project | 2018-07-06 | 240 |  | 300
10480 | Engineering | 2018-05-06 | 480 |  | 500
10480 | Engineering | 2018-06-06 | 480 |  | 480
10480 | Engineering | 2018-07-06 | 120 |  | 60
10480 | Operations | 2018-05-06 | 120 | 30000 | 120 | 25000
10480 | Operations | 2018-06-06 | 120 | 20000 | 120 | 17000
10480 | Operations | 2018-07-06 | 240 | 7000 | 26 | 15000